## Project Information
I. Requirements
Công ty Phone Hub một công ty chuyên kinh doanh về các thiết bị di động trong nhiều năm nay và đã có một lượng khách hàng nhất định. Để mở rộng hoạt động kinh doanh của mình, công ty mong muốn xây dựng một hệ thống thương mại điện tử nhằm mở rộng phạm vi kinh doanh trên mạng Internet. Website bán hàng trực tuyến của Phone Hub là loại hình kinh doanh qua mạng bằng cách xây dựng một trang web bán hàng để mọi người có thể vào đó xem các sản phẩm mà Phone Hub phân phối, có thể lựa chọn sản phẩm để mua hàng. Với trang web bán hàng trực tuyến, nhà kinh doanh sẽ đưa thông tin của các thiết bị di động lên trang web của mình. Việc đưa thông tin lên cũng phải theo một trật tự hợp lý, đảm bảo tính thẩm mỹ, khoa học.

## Team
TEAM DEVELOPMENT STRUCTURE
No. | Name | Account | Roles | DateStart | Date End
1 | Nguyễn Văn Đức Tính | ngtinhs | Product Owner / Dev | 2023-02-17
2 | Phạm Lê Anh Tú | Tupham | ScrumMaster / Dev | 2023-02-17
3 | Trần Văn Đạt | Dat | Team Lead / Dev | 2023-02-17

## Product backlog
E-COMMERCE PROJECT - PRODUCT BACKLOG
Story ID | Story Name | Points
81
Actor: Guest(Khách vãng lai)
1 | View HomePage | 4
2 | View Product list | 4
3 | View Product details | 2
4 | View Product Compare | 2
5 | Manage Shopping Cart (Add, Increase, Decrease, Remove) | 4
6 | Registration | 4
7 | Chat with Sale | 4
Actor: Customer (Khách hàng)
8 | Login | 2
9 | Make Orders | 2
10 | Order Management (View, Cancel request) | 6
11 | View Shipping Progress | 2
12 | Online Payment | 4
13 | Logout | 1
Actor: Order Processing (Nhân viên xử lý đơn hàng)
14 | View New Order | 2
15 | Order Management (View, Short, Update) | 4
16 | Shipping Management | 6
17 | Payment Mornitoring | 2
Actor: Sale Manager(Nhân viên quản lý bán hàng)
19 | Product Management | 6
20 | Store Management | 4
21 | Inventory Management | 6
22 | Price Management | 4
23 | Promotion Management | 4
Actor: Administration (Quản trị viên)
24 | User Management | 6

## Sprint backlog
E-COMMERCE PROJECT - SPRINT BACKLOG
Story ID | Story Name | Points | Name Of Dev | Start Date | Endate | Act Start Date | ActEndate | Act Points | Notes
16
Sprint 1
1 | View HomePage | 4
2 | View Product list | 4
3 | View Product details | 2
4 | View Product Compare | 2
5 | Manage Shopping Cart (Add, Increase, Decrease, Remove) | 4
6 | Registration | 4
7 | Chat with Sale | 4